## Construction Schedule Template
CONSTRUCTION SCHEDULE
Project Name:
Strart Date:
Total Duration:
Project Manager:
End Date:
TASK DESCRIPTION | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION | COMMENTS
Planning | Complete |  | 2025-09-21 | 2025-09-30 | 10 | ____________
Raw Material Accumulation | Complete |  | 2025-10-01 | 2025-10-06 | 6 | ____________
Basement Creation | Complete |  | 2025-10-06 | 2025-10-24 | 19 | ____________
Floors Creation | Complete |  | 2025-10-25 | 2025-10-29 | 5 | ____________
Light Fittings | Complete |  | 2025-11-01 | 2025-11-13 | 13 | ____________
Sewage Pipelines | Complete |  | 2025-11-13 | 2025-11-15 | 3 | ____________
Painting | In Progress |  | 2025-10-25 | 2025-12-05 | 20 | ____________
Accessories Installation | In Progress |  | 2025-11-19 | 2025-12-10 | 22 | ____________
AC Installation | In Progress |  | 2025-10-29 | 2025-12-09 | 5 | ____________
Fire Extingushers | In Progress |  | 2025-11-22 | 2025-12-15 | 24 | ____________
Parking Space | Not Started |  | 2025-11-29 | 2025-12-20 | 22 | ____________
Appliances | On Hold |  | 2025-12-10 | 2025-12-22 | 13 | ____________
Plumbing | In Progress |  | 2025-12-10 | 2025-12-15 | 6 | ____________
Final Inspections | Not Started |  | 2025-12-27 | 2025-12-30 | 4 | ____________
Wrap up | Not Started |  | 2025-12-03 | 2025-12-21 | 19 | ____________
House Cleaning | Not Started |  | 2026-01-03 | 2026-01-23 | 21 | ____________
Complete | Not Started |  | 2026-01-03 | 2026-01-17 | 15 | ____________