## Project Risk Register
PROJECT NAME: M65 LABELLING MACHINE PROTOTYPE |  |  |  | PROJECT #: M65-2022 |  | PROJECT VALUE:
CLIENT NAME: HERRMA LTD |  |  |  | START DATE: 01/04/2022 |  | 125000
PROJECT MANAGER: JOHN DOE |  |  |  | END DATE: 01/12/2022
DATE | # | RISK DETECTED | PROJECT IMPACT | CATEGORY | RISK RATING | RESPONSIBLE | STATUS | CLOSURE DATE
2022-04-05 | R000 | Chip manufacturing worldwide crisis | Boards delay - more than 3 weeks | Supplies | HIGH | John Richardson | Ongoing
2022-04-09 | R001 | Emergency equipment renovation | Closing offices for 2 days - delay | Infrastructure | MEDIUM | Isabella Grey | Finished | 2022-04-14
2022-04-10 | R002 | Additional permits related to RoHS | Not able to deliver products | Permits | HIGH | John Forester | Not Started
PROJECT RISK REGISTER