## Issues_Tracking_Log
ISSUE MANAGEMENT LOG
Project Name: ______________________________________________________________
National Center ____________________________________________________________
Project Manager Name: _____________________________________________________
Project Description: _________________________________________________________
Current Status | Priority | Issue Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Impact Summary | Action Steps | Issue Type | Date Identified | Assoc ID | Entered By | Actual Resolution Date | Final Resolution & Rationale
Open | Critical | EXAMPLE: Issues raised by board members about the financial viability of the project are preventing the project from moving forward as planned. |  |  | Yes | EXAMPLE: Potential project stoppage | EXAMPLE: Meet with board members to clarify the project finances | Informational | 2006-01-01 |  | John Doe |  | EXAMPLE: The project team met with board members to clarify the project finances, allowing the project to move forward as planned.
Work In Progress | High | EXAMPLE: The project is short on a specific skill set. |  |  | No | EXAMPLE: Possibility of project work not completed on time | EXAMPLE: Add staff to fill the skills gap. | Procedural | 2006-01-01 |  | Jane Doe |  | EXAMPLE: Staff was added to the project to fill the skills gap.
Closed | Medium | EXAMPLE: Negotiations with functional managers in an organization competing for scarce human resources are forecasted to delay project completion. |  |  | Yes | EXAMPLE: Possability of project work not completed on time | EXAMPLE: Additional negotiation | System | 2006-01-01 |  | Tom Doe |  | EXAMPLE: Negotiations ended satisfactorily before they caused project delays.
| Low | [6 empty] | Other
Open | Critical | EXAMPLE: Issues raised by board members about the financial viability of the project are preventing the project from moving forward as planned. |  |  | Yes | EXAMPLE: Potential project stoppage | EXAMPLE: Meet with board members to clarify the project finances | Informational | 2006-01-01 |  | John Doe |  | EXAMPLE: The project team met with board members to clarify the project finances, allowing the project to move forward as planned.
Note on B8: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
Note on C8: • Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
Note on D8: • Issue Description: This column should be populated with a description of the issue.
Note on E8: • Assigned To Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
Note on F8: • Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
Note on G8: • Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on H8: • Impact Summary: This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
Note on I8: • Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on J8: • Issue Type: This column should be populated with the issue type. Valid options include the following: FRI, Procedural, System, Other. These are defined as follows: o Informational: The issue was generated and logged in response to a request for information external to the immediate project/project team. o Procedural: The issue impacts process or procedure. o System: The issue impacts systems (hardware or software). o Other: The issue impacts other areas.
Note on K8: • Date Identified: This column should be populated with the date that the issue was identified.
Note on L8: • Associated Milestone ID(s): This column should contain the project ID of any associated milestones that may be impacted by an issue or that the issue is dependant upon for resolution. Please note, this value may require coordination with other program/project managers or the PMA.
Note on M8: • Entered By: This column should be populated by the name of the individual who first identified the issue.
Note on N8: • Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
Note on O8: • Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.