## Weekly Task List (M-F)
WEEKLY TASK LIST
| TASK NAME | STATUS | DUE DATE | TASK TYPE | ASSIGNED TO | HOURS BUDGETED | ACTUAL HOURS
Monday | Write email series | 🏃 In progress | 2023-01-08 | Content | Rebecca | 4 | 3.5
| Wireframe landing page | ⚠️Not started | 2023-01-10 | UX | Aaron | 2 | 2
| Design campign board | ✅ Complete | 2023-01-13 | Design | Micah | 12 | 13.5
| Build checkout page | ❌ On hold | 2023-01-11 | Development | Emily | 4.5
Tuesday | Write blog post | ⚠️Not started | 2023-01-16 | Content | Rebecca | 6
| Revamp online calculator | 🏃 In progress | 2023-01-18 | UX | Aaron | 12 | 10
| Layout new homepage | 🏃 In progress | 2023-01-19 | Design | Micah | 18 | 15
| Build free trial form | ✅ Complete | 2023-01-21 | Development | Emily | 24 | 21
Wednesday | Write monthly newsletter | 🏃 In progress | 2023-01-23 | Content | Rebecca | 4 | 4
| Writeframecheckout process | ⚠️Not started | 2023-01-25 | UX | Aaron | 6 | 5.5
| Design email campaign | ❌ On hold | 2023-01-26 | Design | Micah | 4
| Update mobile app | ✅ Complete | 2023-01-27 | Development | Emily | 18 | 18