## Project Plan and Gantt
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20%
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
Set Kick-Off Meeting | Alex B. | 2022-09-02 | 2022-09-03 | 1 | Complete
Agree on Objectives | Frank C. | 2022-09-03 | 2022-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2022-09-07 | 2022-09-12 | 5 | Complete
Hardware Reqs. | Jacob S. | 2022-09-09 | 2022-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2022-09-11 | 2022-09-15 | 4 | In Progress
Staffing | Alex B. | 2022-09-16 | 2022-09-17 | 1 | In Progress
Technical Reqs. | Frank C. | 2022-09-17 | 2022-09-21 | 4 | Not Started
DB Development | Shari W. | 2022-09-22 | 2022-09-24 | 2 | Not Started
API Development | Shari W. | 2022-09-23 | 2022-09-27 | 4 | Not Started
UI Client | Alex B. | 2022-09-25 | 2022-09-29 | 4 | Not Started
Testing | Kennedy K. | 2022-09-24 | 2022-10-02 | 8 | Not Started
Dev. Complete | Jacob S. | 2022-10-02 | 2022-10-05 | 3 | Not Started
Hardware Config. | Alex B. | 2022-10-05 | 2022-10-07 | 2 | Not Started
System Testing | Kennedy K. | 2022-10-06 | 2022-10-09 | 3 | Not Started
LAUNCH |  | 2022-10-09 | 2022-10-10 | 1

## Project Plan and Gantt - BLANK
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Overdue
|  |  |  | 0 | In progress
|  |  |  | 0 | In progress
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Stakeholder List
STAKEHOLDER LIST
NAME | POSITION | ROLE IN PROJECT | EMAIL ADDRESS | REQUIREMENTS | EXPECTATIONS
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK | % COMPLETE | BASE COST | COST | ACTUAL COST | % BUDGET SPENT
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%
l

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE | DELIVERABLE | DESCRIPTION | DELIVERY METHOD | FREQUENCY | OWNER | AUDIENCE
Presentation | 15-minute PowerPoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team