## Commercial Construction Sch.
COMMERCIAL CONSTRUCTION SCHEDULE
PROJECT TITLE |  |  | PROJECT MANAGER
COMMERCIAL CONSTRUCTION XPRESS |  |  | JOHN DOE
LOCATION |  |  | CLIENT
35 MAIN BUILDING AVENUE, ROSEVELT |  |  | BUILDING INVESTMENT HOLDING LTD
TASK NAME | STATUS | ASSIGNED TO |  | START DATE | END DATE | DURATION in days
1.0 SITE PREPARATION | Completed | Management |  | 2022-05-01 | 2022-05-30 | 30
1.1 Implamentation of drainage | Completed | Drainage LLC |  | 2022-05-01 | 2022-05-08 | 8
1.2 Removal of vegetation | Completed | Machinery team |  | 2022-05-02 | 2022-05-16 | 15
1.3 Inspection of structural lines | Completed | Engineering team |  | 2022-05-18 | 2022-05-30 | 13
2.0 FOUNDATION | Completed | Construction team 1 |  | 2022-06-01 | 2022-06-10 | 10
3.0 FRAMING | In Process | Construction team 2 |  | 2022-06-11 | 2022-07-20 | 40
4.0 ROOFING, SIDING AND HVAC | Pending | Construction team 3 |  | 2022-07-21 | 2022-10-20 | 92
4.1 Roofing | Not Started | Construction team 3 |  | 2022-07-21 | 2022-08-04 | 15
4.2 Siding | Not Started | Construction team 3 |  | 2022-07-21 | 2022-09-10 | 52
4.3 HVAC | Not Started | Construction team 3 |  | 2022-09-10 | 2022-10-20 | 41
5.0 INTERIOR | Not Started | Construction team 4 |  | 2022-10-21 | 2022-11-12 | 23
5.1 Hardwoods | Not Started | Construction team 4 |  | 2022-10-21 | 2022-10-22 | 2
5.2 Tile | Not Started | Construction team 4 |  | 2022-10-22 | 2022-10-25 | 4
5.3 Cabinets | Not Started | Construction team 4 |  | 2022-10-22 | 2022-10-28 | 7
5.4 Plumbing -hang sinks | Not Started | Construction team 4 |  | 2022-10-26 | 2022-11-01 | 7
5.5 Stone Counters | Not Started | Construction team 4 |  | 2022-11-01 | 2022-11-07 | 7
5.6 Schedule Buffer | Not Started | Construction team 4 |  | 2022-11-01 | 2022-11-08 | 8
5.7 Decks | Not Started | Construction team 4 |  | 2022-11-02 | 2022-11-05 | 4
5.8 Laundry/furnace room flooring | Not Started | Construction team 4 |  | 2022-11-05 | 2022-11-12 | 8
6.0 EXTERIOR | Not Started | Special team 1 |  | 2022-11-12 | 2022-12-15 | 34
7.0 UTILITIES | Not Started | Electrical team |  | 2022-11-12 | 2022-12-18 | 37
8.0 LANDSCAPING | Not Started | Landscaping team |  | 2023-01-05 | 2023-01-28 | 24
9.0 LOREM IPSUM | Not Started | Person 1 |  | 2023-01-10 | 2023-02-02 | 24
9.1 Subtask description | Not Started | Person 1 |  | 2022-01-10 | 2022-01-28 | 19
9.2 Subtask description | Not Started | Person 1 |  | 2022-01-29 | 2022-02-02 | 5