## Construction Project Timeline
CONSTRUCTION PROJECT TIMELINE
PROJECT TITLE |  |  |  | START
|  |  |  | 2025-09-21 |  | PROJECT DURATION
PROJECT MANAGER |  |  |  | END |  | 254
2026-06-01
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION | COMMENTS | STATUS
Planning | Complete | Name | 2025-09-21 | 2025-09-30 | 10 | COMMENT | Not Started
Demo Prep | Complete | Name | 2025-10-01 | 2025-10-06 | 6 | COMMENT | In Progress
Demolition | Complete | Name | 2025-10-06 | 2025-10-24 | 19 | COMMENT | Complete
Excavation | Complete | Name | 2025-10-25 | 2025-10-29 | 5 | COMMENT | On Hold
Concrete | Complete | Name | 2025-11-01 | 2025-11-13 | 13 | COMMENT
Pre backfill | Complete | Name | 2025-11-13 | 2025-11-15 | 3 | COMMENT
Framing | In Progress | Name | 2025-10-25 | 2025-12-05 | 42 | COMMENT
Roof | In Progress | Name | 2025-11-19 | 2025-12-10 | 22 | COMMENT
Plumbing | In Progress | Name | 2025-10-29 | 2025-12-09 | 42 | COMMENT
Windows | On Hold | Name | 2025-11-22 | 2025-12-15 | 24 | COMMENT
HVAC | In Progress | Name | 2025-11-29 | 2025-12-20 | 22 | COMMENT
Electrical | In Progress | Name | 2025-12-10 | 2025-12-22 | 13 | COMMENT
A/V | Complete | Name | 2025-12-10 | 2025-12-15 | 6 | COMMENT
House wrap | Complete | Name | 2025-12-27 | 2025-12-30 | 4 | COMMENT
Insulation | In Progress | Name | 2025-12-03 | 2025-12-21 | 19 | COMMENT
Drywall | In Progress | Name | 2026-01-03 | 2026-01-23 | 21 | COMMENT
Exterior stone | In Progress | Name | 2026-01-03 | 2026-01-17 | 15 | COMMENT
Exterior case work | Not Started | Name | 2026-01-04 | 2026-01-13 | 10 | COMMENT
Laundry/furnace room flooring | In Progress | Name | 2026-02-16 | 2026-03-11 | 24 | COMMENT
Hardwoods | In Progress | Name | 2026-01-19 | 2026-03-10 | 51 | COMMENT
Tile | On Hold | Name | 2026-02-03 | 2026-02-14 | 12 | COMMENT
Cabinets | In Progress | Name | 2026-01-18 | 2026-03-06 | 48 | COMMENT
Plumbing -hang sinks | In Progress | Name | 2026-02-16 | 2026-02-23 | 8 | COMMENT
Interior doors | Complete | Name | 2026-02-25 | 2026-03-09 | 13 | COMMENT
Millwork | Complete | Name | 2026-02-15 | 2026-02-17 | 3 | COMMENT
Interior painting | In Progress | Name | 2026-02-28 | 2026-04-14 | 46 | COMMENT
Stone Counters | In Progress | Name | 2026-03-21 | 2026-03-31 | 11 | COMMENT
Schedule Buffer | In Progress | Name | 2026-02-28 | 2026-03-10 | 11 | COMMENT
Decks | In Progress | Name | 2026-02-28 | 2026-03-18 | 19 | COMMENT
Interior doors- hang & hardware | Complete | Name | 2026-05-03 | 2026-05-13 | 11 | COMMENT
Appliances | Complete | Name | 2026-05-02 | 2026-05-03 | 2 | COMMENT
Plumbing | In Progress | Name | 2026-05-02 | 2026-05-05 | 4 | COMMENT
Electrical | In Progress | Name | 2026-05-03 | 2026-05-11 | 9 | COMMENT
Bathroom Glass | In Progress | Name | 2026-05-09 | 2026-05-13 | 5 | COMMENT
Garage Door dress up | Not Started | Name | 2026-05-13 | 2026-05-18 | 6 | COMMENT
FINAL Inspections | In Progress | Name | 2026-05-02 | 2026-05-02 | 1 | COMMENT
Wrap up | In Progress | Name | 2026-05-09 | 2026-06-05 | 28 | COMMENT
House Cleaning | On Hold | Name | 2026-05-29 | 2026-06-10 | 13 | COMMENT
Complete | In Progress | Name | 2026-06-10 | 2026-06-10 | 1 | COMMENT