## Instructions
The Stakeholder Analysis Tool is used to identify stakeholders, and to assess their influence and favorability.
Stakeholders are individuals and groups, both inside and outside the Challenge team/start-up, who can:
-influence the success of the business plan and start-up
-be impacted by the new start-up
-actively support the start-up through funding, mentoring, etc.
The Stakeholder Analysis Process
1.Brainstorm a list of Stakeholders, asking, “who can influence the success of my business plan and startup and who can be impacted by the project?” Segment the stakeholders into meaningful clusters as appropriate (functions, regions,etc.)
2.Ask, “to what degree do they have the power to influence the success of the ultimate startup?” Use the 1-5 scale shown on the Template (COLUMN 0)
3.Next ask, “what is this stakeholder’s current level of commitment to the startup? How Favorably do they view the startup?” Use the 1-5 scale shown on the Template (COLUMN P)
4.Ask, “for our start-up, what does success look like to this stakeholder, what would they consider to be wins?” (COLUMN T)
5.Identify proactive actions to achieve these “wins”, and to engage them to increase their favorability.
Overview of RACI Matrix
The meaning of the acronym RACI…
| R = Responsible | Owner of the task/project - person responsible for completing the task
| A = Accountable | Person who finally signs off on a task
| C = Consulted | Person who has the information and/or capability to complete the work. May provide input that aids in the completion of a task
| I = Informed | Must be notified of a project/task/event but does not need to be consulted
RACI Best Practices
1. Multiple parties can be Responsible ("R"), Consulted ("C") or Informed ("I") but only 1 person can be Accountable ("A") for 1 task
2. It is possible for one person to be both Responsible and Accountable for a task ("R,A")
3. If the process box spans multiple swimlanes in the flow, all of these parties should be represented in the RACI,
or if the roles in the RACI do not match the process flow, please highlight the tasks and we will go back and revise the flows

## Stakeholder Analysis
Stakeholder Analysis Template
|  | Stakeholder Type |  |  |  | Stakeholder Impact
Group | Key Representative | Accountable | Responbile | Consluted | Informed | Outcome Accountable | Outcome Impacted | Output End User | Internal/External | Priority (High/ Med/ Low) | Direct/Indirect Involvement | Relationship with / Interest in start-up | Goals / Success Criteria for Stakeholder | Power/ Influence: | Current Level of Commitment | What does the start-up need from this group? | Impact of Start-up | Potential Issues or Concerns | What does this Stakeholder need to engage with our start-up? | Management Strategy / Method of Communication
Patient | Dr. Jones | b |  |  |  | b | b |  | Internal | High | Direct | Project Owner | Improve Standard of Care | 1 = This stakeholder has little power/ influence over the start-up | 1 = Negative, actively or subversively working against | Funding | (1)Budgetary (2)Solution review (3)Credibility | Specificity. Fit for purpose. User engagement. | Scope definition. Cost definition. | Review meeting
VC | Dr. Miller | b | b |  | b | b | b |  | Internal | High | Direct | Manager | Profit | 2 = This stakeholder has some influence over the start-up | 2 = Moderately negative, passive resistance | Direction. Information. Support. Contacts | Time. Credibility. Review. Documentation. | Responsiveness. Awareness/understanding of options. |  | Weekly phone call. Ad-hoc face to face meetings. Workshops
Non-Dilutive Funder | [13 empty] | 3 = This stakeholder has moderate influence over the start-up | 3 = Neutral
Payer | [13 empty] | 4 = This stakeholder has major influence over the start-up | 4 = Moderately positive, passive support
Collaborator | [13 empty] | 5 = Without support from this stakeholder, the start-up is doomed to fail | 5 = This is great, I'm in, an active supporter
Key Opinion Leader
Notes
1. Hide columns you don't need, in order to make this template easier to read
2. Aggregate columns or pick out specific ones if reporting the analysis to reviewers or discussion groups. This table is probably too detailed to fit into most A4 sized documents.