## Project Risk Assessment SAMPLE
BUSINESS PROJECT RISK ASSESSMENT SAMPLE TEMPLATE
PROJECT ID | PROJECT NAME | [6 empty] | PROJECT MANAGER | ASSESSED BY | ASSESSMENT DATE
PROJECT DESCRIPTION | [8 empty] | APPROVED BY | APPROVAL DATE
Rate Probability and Impact Levels on a scale of 1 to 3 | [5 empty] | ––––––– DO NOT ALTER –––––––
REF ID | HAZARD DESCRIPTION | PROJECT PHASE | IMPACT DESCRIPTION Time, Cost, Performance | PROBABILITY | IMPACT | SCORE | RISK LEVEL | CURRENT RISK MITIGATION AND CONTROL MEASURES | ACTION PLAN | ACTION OWNER | STATUS | COMPLETION DATE | LEVEL | RATING MATRIX |  |  |  | RATING_NO | RATING_NAME
1.0 | Supplier going out of business | Planning and Execution | Project disruption and server failure, which will delay progress and cost $8,500 to set up new systems | 3 | 3 | 9 | HIGHEST | Systems are backed up every 30 minutes, and extra equipment is available | Form new partnerships with multiple suppliers | Annie Lee | In Progress | 00/00/0000 | 1 | 3 | 3 | 6 | 9 | 1 | LOWEST
|  |  |  | 3 | 2 | 6 | MEDIUM HIGH | [5 empty] | 2 | 2 | 2 | 4 | 6 | 2 | VERY LOW
|  |  |  | 2 | 2 | 4 | MEDIUM LOW | [5 empty] | 3 | 1 | 1 | 2 | 3 | 3 | LOW
|  |  |  | 1 | 3 | 3 | LOW | [7 empty] | 1 | 2 | 3 | 4 | MEDIUM LOW
|  |  |  | 1 | 2 | 2 | VERY LOW | [10 empty] | 6 | MEDIUM HIGH
|  |  |  | 1 | 1 | 1 | LOWEST | [10 empty] | 9 | HIGHEST

## Project Risk Assessment BLANK
BUSINESS PROJECT RISK ASSESSMENT
PROJECT ID | PROJECT NAME | [6 empty] | PROJECT MANAGER | ASSESSED BY | ASSESSMENT DATE
PROJECT DESCRIPTION | [8 empty] | APPROVED BY | APPROVAL DATE
Rate Probability and Impact Levels on a scale of 1 to 3 | [5 empty] | ––––––– DO NOT ALTER –––––––
REF ID | HAZARD DESCRIPTION | PROJECT PHASE | IMPACT DESCRIPTION Time, Cost, Performance | PROBABILITY | IMPACT | SCORE | RISK LEVEL | CURRENT RISK MITIGATION AND CONTROL MEASURES | ACTION PLAN | ACTION OWNER | STATUS | COMPLETION DATE | LEVEL | RATING MATRIX |  |  |  | RATING_NO | RATING_NAME
[13 empty] | 1 | 3 | 3 | 6 | 9 | 1 | LOWEST
[13 empty] | 2 | 2 | 2 | 4 | 6 | 2 | VERY LOW
[13 empty] | 3 | 1 | 1 | 2 | 3 | 3 | LOW
[15 empty] | 1 | 2 | 3 | 4 | MEDIUM LOW
[18 empty] | 6 | MEDIUM HIGH
[18 empty] | 9 | HIGHEST

## Score Keys
PROBABILITY KEY |  |  | IMPACT KEY
| 1 | Unlikely |  | 1 | Low
| 2 | Likely |  | 2 | Medium
| 3 | Very Likely |  | 3 | High