## Stakeholder Analysis
Stakeholder Analysis Template
|  | Stakeholder Type |  |  |  | Stakeholder Impact
Group | Key Representative | Accountable | Responbile | Consluted | Informed | Outcome Accountable | Outcome Impacted | Output End User | Internal/External | Priority (High/ Med/ Low) | Direct/Indirect Involvement | Relationship with / Interest in project | Goals / Success Criteria | Impact on Project | What does the project need from this group? | Impact of Project | Potential Issues or Concerns | Needs | Management Strategy / Method of Communication
VP Product Development | Cheryl Lynn | b |  |  |  | b | b |  | Internal | High | Direct | Project Owner | On time, to budget | Over-all control | Approval | (1)Budgetary (2)Solution review (3)Credibility | Specificity. Fit for purpose. User engagement. | Scope definition. Cost definition. | Review meeting
IT Team | Michael Lee | b | b |  | b | b | b |  | Internal | High | Direct | Manager | Issue visibiilty. User satisfaction. | Day-to-day management | Direction. Information. Support. Contacts | Time. Credibility. Review. Documentation. | Responsiveness. Awareness/understanding of options. | Regular meetings. Single point of contact.To understand and approve solution and to be kept informed of all developments. | Weekly phone call. Ad-hoc face to face meetings. Workshops
Notes
1. Hide columns you don't need, in order to make this template easier to read
2. Aggregate columns or pick out specific ones if reporting the analysis to reviewers or discussion groups. This table is probably too detailed to fit into most A4 sized documents.