## Dashboard
Highlights from Quarter 2
● This report describes CQC’s performance across Quarter 2 of the 2010-11 reporting year. Comparative data is included for Quarter 1 to demonstrate progress across the year; the full Quarter 1 performance scorecard was reported to the Board in September 2010. ● Our performance across the quarter is predominantly Amber - the registration programme and recruitment issues have impacted the performance of other areas of the business, alongside other issues being managed. ● Resources have been focused on processing ASC and IHC re-registrations under the Health and Social Care Act; of the applications received, 93% of providers received all notices of decision by 30 September. ● There has been a linked reduction in inspection and enforcement activity under the Care Standards Act 2000, and CSA registration processing times were adversely impacted towards the end of the quarter.
Forward look to Quarter 3
● From 1 October 2010, all health and adult social care providers are legally responsible for making sure they meet essential standards of quality and safety and must be licensed with CQC; we will undertake a series of risk-based reviews of NHS, ASC and IHC providers, assessing them against the same set of essential standards of quality and safety. ● Our registration programme continues; we have to finalise the registration of the ASC and IHC providers who were invited to re-register by 30 September, and commence the next tranche of activity, to register dentists and private ambulance services by March 2011. ● We have created a new headquarters structure which will go live on 1 November enabling us to maintain the focus of our work on supporting registration and compliance. ● Over the coming months we will also be focusing on the impact of wider changes on CQC resulting from the ALB review and White Paper and considering how our strategy needs to evolve alongside work to define our organisational benefits and planning priorities for the future.
Objective | Last Period | This Period | Trend
1.1.1 Registration of providers | A | A | D
1.1.2 Manage the re-registering of providers | A | A | D
1.2 Deliver programme to monitor compliance | A | A | D
1.3 Assessing the quality of health and social care provision and commissioning (AoQ) | A | A | D
1.4 Deliver Mental Health Act / SOAD visiting effectively | R | R | D
1.5 Deliver other statutory inspection responsibilities | G | G | D
1.6 Publish information on quality of health and social care services | A | A | D
Objective | Last Period | This Period | Trend
2.1 Effective Shared Services Centre | G | G | D
2.2 EDHR compliance | G | G | D
2.3 Communications | G | G | D
Objective | Last Period | This Period | Trend
3.1 Effective and well supported workforce | A | A | D
3.2 Deliver high quality service to our customers | NR | NR
3.3 Engaging effectively with stakeholders | NR | NR
Objective | Last Period | This Period | Trend
4.1 Income/ expenditure is controlled and planned | G | G | D
4.2 Develop IS and ICT | G | G | D
4.3 Deliver high standard of corporate governance | A | A | D
Objective | Last Period | This Period | Trend
5.1 Deliver Registration Programme | A/R | A | ­
5.2 Deliver Assessments of Quality Programme | A | NR
5.3.1 Deliver Field Force Model Implementation Programme | G | A/G | ¯
5.3.2 Deliver HQ Review Programme | G | A | ¯
5.4 Deliver Shared Service Transformation Programme | A | G | ­
5.5 Deliver Modernising Mental Health Act Programme | A | A | D
5.6 Deliver People's Voices Programme | A | NR
Details about changes in performance ratings follow in the progress report, with key performance indicators shown in the performance scorecard
1. Regulatory Activity
2. Supporting Activities
3. Stakeholders
4. Financial and other resources
Performance Dashboard - Quarter 2 (July - September 2010)
5.Change

## Scorecard
**DRAFT** CQC Balanced Scorecard - May 2010 **DRAFT**
3. STAKEHOLDERS
Objective | Target | Last period | This period | Trend | Supporting detail | Objective | Target | Last period | This period | Trend | Supporting Detail
1.1.1 Registration of providers | [5 empty] | 4.1 Income/ expenditure is controlled and planned
% of registrations completed in set time period (adult social care) | 90% | 90% | 92% | ­ | Performance remains on target, with improvements in the timeliness of manager registrations. | On/ off target within capital, revenue, transition | Variance | £10.4m | £4.2m |  | The cumulative expenditure to the end of Quarter 2 is £92.4m against a budget of £107m (favourable variance of £14.6m).
% of registrations completed in set time period (independent healthcare) | 90% | 45% | 53% | ­ | Performance issues remain but this is mainly due to low numbers and the cessation of the Care Standards Act. | Cost of finance function as a % of the business | 1.5% | 1.3% | 1.4% |  | Internal target 1.5%. Average finance function cost across H&SC ALBs is 4.6%
1.1.2 Manage the re-registering of providers (objective will complete in Q3)
Total number of providers served with all Notices of Decision | 10659 | 0 | 9922 |  | Target is applications received by 30/09. | 4.2 Develop IS and ICT
Total number of Notices of Decision issued |  | 0 | 40043 |  | NODs are issued for each registered service (sent to 10,242 separate providers) | % ICT service incidents closed within target | 99% | 99.6% | 99.7% | ­
Total number of certificates issued |  | 0 | 0 |  |  | Cost of IT service as a % of the business | 5.1% | 10.5% | 10.09% | ­
1.2 Deliver programme to monitor compliance
Planned compliance reviews completed vs plan | 90% | 11 | 45 |  | Detailed scheduling is underway to develop plans for Q3&Q4. Unable to report activity against target for Q2 due to system scheduling issues. | 4.3 Deliver high standard of corporate governance
Responsive reviews completed vs plan | 100% | 23 | 32 |  |  | Information requests closed within target time | 100% | 94.4% | 96.8% | ­ | Improved request handling, with a higher number of requests received in Quarter 2
Conditions reduce over time | <22 | 18 | 10 | ­ | 12 of 22 NHS trusts have now had all conditions removed | Requests for internal review (complaints against FOI and DPA decisions) | 0 | 7 | 6 | ­
No. of services subject to enforcement action that return to enforcement within 24 months |  | NR | 6 |  |  | Serious Untoward Incidents reported to Information Commissioner's Office (information handling) | 0 | 2 | 2 | D
No. enforcement actions in period |  | 171 | 74 | ¯ | Breakdown of Enforcement activity included in Spotlight Report | Health and Safety - no. of workplace accidents |  | NR | 8
[6 empty] | Stage 1 requests received |  | 27 | 25 |  | Slight reduction in overall demand on the Complaints Review Service
1.3 Assessing the quality of health and social care provision and commissioning | [5 empty] | Stage 2 requests received |  | 14 | 9
Reviews and Studies - project status | 100% | G | A/R | ¯ | Resourcing issues across all reviews | Number of complaints taken to external investigation |  | 1 | 0 |  | 1 investigation commenced in Q1 which was closed in Q2
CSA inspections vs plan | 90% | 82% | 100% | ­
1.4 Deliver Mental Health Act/SOAD visiting effectively | [5 empty] | 4. FINANCE & OTHER RESOURCE
Mental health visits completed vs target | 100% | 83% | 100% | ­ |  | Objective | Target | Last period | This period | Trend | Supporting Detail
% Second Opinions completed within set time | 100% | 31% | 36% | ­ | Improvement for medication and CTO opinions, issues being addressed through modernisation project | 5.1 Deliver Registration Programme
[6 empty] | Programme progress - % milestones achieved | 100% | A/R | A | ­ | Tranche 3 data validation stage opened, tranche 2 registrations being completed with final NODs and certificates due to be issued from 1 October. Programme is currently being affected by resource and system issues, being closely managed.
1.5 Deliver other statutory inspection responsibilities | [5 empty] | Tranche 1 - NHS |  | NR | A/G
% inspections completed vs plan | 100% | G | G | D | Consolidates inspection types, all performing in line with expectations | Tranche 2 - ASC/ IHC |  | NR | A
[6 empty] | Tranche 3 - Dental practitioners and private ambulances |  | NR | A
1.6 Publish information on quality of health and social care services | [5 empty] | Tranche 4 - GP Practices |  | NR | A/G
% key publications on target | 100% | A | A | D | All published to time, provider feedback required to assess reception | 5.2 Deliver Assessments of Quality Programme
[6 empty] | Programme progress - % milestones achieved vs target | 100% | A | NR |  | Not reported for Q2. Programme being restructured to reflect Regulatory Development activity.
5.3.1 Deliver Field Force Programme
Objective | Target | Last period | This period | Trend | Supporting Detail | Programme progress - % milestones achieved vs target | 100% | G | A/G | ¯ | RAG decrease as operations readiness being closely managed, approaching programme closure
2.1 Effective Shared Services Centre | [5 empty] | 5.3.2 Deliver HQ Review Programme
Call handling within target 20 seconds | 80% | 92.1% | 96.4% | ­ | Call handling has improved despite significant increase in volume from 33k to 86k | Programme progress - % milestones achieved vs target | 100% | G | A | ¯ | RAG decrease as staffing issues affecting urgent deliverables
Safeguarding call handling within target 20 seconds | 90% | 96.4% | 95.9% | ¯ |  | 5.4 Deliver Shared Service Transformation Programme
Registration processing vs target | G | G | G | ­ | Faster processing of registrations | Programme progress - % milestones achieved vs target | 100% | A | G | ­ | Issues resolved, progressing well
5.5 Deliver Modernising Mental Health Act Programme
2.2 EDHR compliance | [5 empty] | Programme progress - % milestones achieved vs target | 100% | A | A | D | Options paper to be reported to Board
Delivery of EDHR strategy on/ off target | 100% | G | G | D |  | 5.6 Deliver People's Voices Programme
2. SUPPORTING ACTIVITIES | [5 empty] | Programme progress - % milestones achieved vs target | 100% | A | NR |  | Programme being restructured
2.3 Communications
Visits to website | - | 1.4m | 1.2m | ¯ | Slight dip in website usage across quarter, feedback mechanism not yet developed
Objective | Target | Last period | This period | Trend | Supporting Detail
3.1 Effective and well supported workforce
Permanent staff | TBC | 1929 | 1887 |  | Impact of Field Force restructure
No. vacancies |  | 91 | 44
Rolling turnover rate |  | 19.2% | 17.08% | ­
Sickness absence |  | 2.58% | 2.42% | ­
Staff grievances upheld |  | NR | 0/11 |  | 11 grievances lodged in Q2, none were upheld
Customer Services and Engagement measures are in development
1. Regulatory Activity
2. Supporting Activities
3. Stakeholders
4. Financial and other resources
5.Change
Performance Balanced Scorecard (Quarter 2 2010)

## Progress report 1
How we have delivered against our Operating Plan - 1 July - 30 September 2010 Regulatory Activity • At the end of Quarter 1 we reported that a prioritisation exercise had been conducted, to focus commission resources on the processing of ASC and IHC re-registrations. By 30 September we had received 10,659 applications from providers, of an expected 12,796, and issued 40,043 Notices of Decision. • In Quarter 2 we undertook 77 compliance reviews of NHS providers, following their registration earlier in the year. 22 were registered with conditions, and by the end of Quarter 2 all conditions had been lifted for 12 of these. The compliance reviews have been focused on those providers registered with conditions or which declared non-compliance in their applications to register. This programme of compliance reviews will continue, expanded to assess whether essential standards are being met in the newly registered ASC and IHC providers. • Preparations for registering dentists and private ambulance providers are underway; guidance has been developed, working with stakeholders and a provider reference group, and events have been hosted alongside web chats, to help reach a wider audience. • The period to 30 September saw us deliver our remaining programme of activities under the Care Standards Act (CSA) 2000. In Quarter 2 we completed 1480 registrations of social care providers and managers under the CSA (over 90% within target processing times), 182 registrations of IHC providers and managers, and all remaining inspections of ASC and IHC providers. • We undertook 74 separate enforcement actions in the period; Charges were laid in the Magistrates' Courts relating to 3 services in respect of offences under The CSA (before its cessation on 30th September 2010). These charges have still to be heard by the Courts. Consequently there has been only one concluded prosecution to date (Quarter 1). These actions are broken down in the spotlight report which follows later in this report. There are currently 177 poor services in total. This equates to 0.73% of the total number of services. • Information upload quantities to the Quality and Risk Profiles are consistent, with over 6500 qualitative pieces of information included in the September upload. 5% of the triggers from the QRPs indicated a high risk impact; these 'red' risks relate to 38 NHS providers (which is approx 10% of all NHS providers). Of the 38 NHS providers that received a red alert in the QRP, 34 of these have been identified by regions in their regional risk registers and have reported as major concerns to the Risk and Escalation Committee. Regions review the information in the QRP and ascertain the correct action to take. • The performance levels of mental health operations remain largely consistent with those reported to the Board previously, with 100% of commissioner visits completed and 36% of second opinions processed within the target time. The Board has received a separate report on the project to modernise the mental health function. Restrictions to recruitment and temporary staff usage have been flagged as key risks to service delivery in this area. • We have published the findings of the ‘community mental health services survey 2010,’ the first since changes were made to the Care Programme Approach in 2008. The findings were generally positive but many of the 17,000 surveyed reported that they had not been involved as much as they would have liked in some aspects of their care. The findings of this survey will be used to inform our continual monitoring of trusts’ compliance with new essential standards of quality and safety.
Quarter 2 - Progress Report 1/4
Supporting Activities • Shared Services have performed well in the period. Call handling performance has increased further since Quarter 1, despite receiving a significantly higher number of calls: the number of safeguarding calls increased from 459 to 1165 (with 95% answered within the target 20 seconds), and registration or other calls increased from 33,813 to 85,284 (96.4% answered within target). • Business as usual registration processing at the processing centre has further improved, with shorter turnaround times. Supporting the re-registration of ASC and IHC providers and managers has placed an increased demand on Shared Services who supported Operations in issuing 9,922 notices of decision by the end of September. Stakeholders • CQC responded to the government Health White Paper and four subsequent consultations in October 2010. • We now have over 48,000 subscribers to our newsletter; the website received slightly fewer visitors in Quarter 2 than Quarter 1, although the average length of visit has increased. • The results of the staff survey were published (76% of the workforce responded) and identified areas to celebrate as well as areas for development. A corporate action plan was launched in August, and local action planning is also underway. • Following the Field Force restructure, and a consultation with headquarters staff in Quarter 1, the programme continues and this period has seen a lot of activity in relation to finalising the new HQ structure and job matching. In the next reporting period the new structure will go live, enabling our HQ activity to align with our new fieldforce structure and new system of registration. Financial and other resources • Recurring revenue expenditure remains within budget; across the year to date we have incurred actual expenditure of £34.8m against a budget of £43.9m. The cumulative expenditure (revenue, transition and capital) to the end of Quarter 2 is £92.4m against a budget of £107m. Further savings have been made on staff costs in the quarter as a result of the freeze on recruitment of permanent staff and a further reduction in the number of temporary staff engaged. Restructuring costs relating to redundancy were high in the quarter, but are as expected and within budget, as the staffing level to support the field force model was put in place. • At 30 September we have 1887 permanent staff and 246 roles which are either vacant or being covered by temporary staff. • The handling of information requests has improved, with 96.8% of responses issued within the target times. To enhance the overall governance of the organisation a lot of work has been carried out within the governance team to implement a new executive committee structure, refine corporate policies and shaping a new internal audit function. • Legal services have continued to support regulatory activity through the provision of advice to the registration programme and in support of enforcement actions being taken.
Quarter 2 - Progress Report 2/4

## Progress report 2
Change • Our change programmes have shown the most movement across performance ratings between Quarters 1 and 2. The Field Force and HQ Review programmes have been affected by issues which have impacted on their delivery performance ratings. The Field Force programme is closely managing operations readiness as it approaches programme closure, and urgent deliverables within the HQ Review programme were affected by staffing issues, but these issues have been resolved since September with the programme status improving. • The performance ratings for Registration and the Shared Services Transformation programme have shown improvement. The Shared Services programme progresses at Green status as issues affecting the programme at the last quarter have been resolved. The end of Quarter 2 represented a key milestone for the Registration programme, as the period of ASC and IHC applications to re-register closed on 30 September. • We have not applied a performance rating to two of the programmes this quarter as the work on Assessments of Quality and People's Voices is being re-scoped which will lead to different programme structures and associated performance reporting. • Projects are being scoped which will support the organisation’s transition to a new operating model in the future. A full estates strategy is being developed, whilst interim building moves in response to changes to the government’s estates portfolio are reported as on target. In terms of the future regulatory model, we are commencing work now to revisit our strategy, in order to reflect changes to the external environment stemming from the White Paper and ALB review. These will be reported as a new programme which is being scoped; previously we have reported on the Assessments of Quality Programme, which will be replaced by these new developments.
Quarter 2 - Progress Report 3/4

## Progress report 3
Management information and data availability - Project update The MI and Performance Reporting project continues to review future reporting requirements and the development of associated MI. By way of update :- Corporate and Directorate Scorecard Development • Both the Executive Team and Board are now receiving regular performance reports in a scorecard based format that seeks to focus on a high level set of metrics that provides an overview of organisational business performance. • In respect of scorecards, draft Directorate Scorecards have now been received from across the business upon which feedback has been provided. Scorecards will be used initially to populate the regular corporate performance report and to pilot Directorate level reporting. • The aim is to have updated scorecards and reporting in place within the pilot areas (to be HR; F&CS; and Governance & Legal) for Q4 and the remaining directorates going live, in line with the new Business Plan, by Q1 2011-12. Improving Management information • This workstream is key to the overall project as it will ensure the relevant processes are in place to improve overall MI across the business both to address key gaps in MI currently, present but to establish more robust BAU arrangements for managing data requests in future. The process to date, overseen by the Steering Group and BDA, has been to • develop for the first time, a comprehensive list of MI requirements from right across the business • prioritise that list of requirements : phase 1 being Registration, Compliance, Enforcement, Mental Health, QRPs and registration tranche activity • undertake a technical system assessment of that list with those in the business to determine data availability or the work necessary to capture data and generate the reports - both through the project (to fill the data gap) and increasingly to take on new data requirements through established BAU processes Implementation Plan Deploying the available resource, the project is delivering to the following summary milestones :- • Working through the ‘long list’ of data requirements, with the assessment of the high priority (operational) areas set out above to complete by Christmas 2010; • Delivery of the above can only be confirmed once the assessment is complete. The plan however is to ensure, as far as possible, delivery of the MI improvements in these priority areas by May 2011 (earlier where reports can be extracted more readily); • Assessment work on the other areas defined in will commence in parallel February 2011 with delivery running in parallel between April and October; again speed of delivery being dependent upon the assessment; • To produce live weekly and monthly data reports, around the key operational metrics defined and linked to the corporate scorecard; the weekly reporting has begun, using available data/systems with the first monthly report to be available mid December. • Work is underway in parallel to fully automate the (above) process and is anticipated to be ready by February 2011; • Scorecard reporting linked to MI development will see the pilot areas going live April 2011 with other areas underway by July 2011.
Quarter 2 - Progress Report 4/4

## Spotlight report
Enforcement activity levels (this does not include activity under the Health and Social Care Act, reporting will commence from 1 October) | Quarter 1 | Quarter 2
Notice of decision issued | 16 | 4
Notice of Decision to cancel registration issued | 1 | 5
Notice of decision to remove a condition of registration | 0 | 1
Notice of proposal to cancel registration issued | 28 | 21
Notice of Proposal to impose conditions of registration | 0 | 3
Notice of proposal to vary conditions issued | 9 | 2
Statutory requirement notice issued | 99 | 22
Warning notice | 18 | 16
Representations
Representations received against noticed of decision issued | 11 received, of which 7 upheld | None received
Prosecutions
Number of successfully concluded prosecutions | 1 | 0
Enforcement – return rate
Services subject to enforcement that return to enforcement within 24 months | 6 (year to date)
Regulatory activity: Enforcement We have seen a large decrease in the activity across enforcement in Quarter 2. This is due to: • The operations directorate’s focus on the Registration of providers under the Health and Social Care Act (2008); • A reduction in inspection activity under the Care Standards Act (2000); • The dissolution of enforcement teams through the reorganisation of operations, with enforcement action being taken by compliance inspectors; In order to free up resource for registration, key inspections (which change quality ratings) were only routinely conducted on poor services. This has resulted in a lack of downward ratings from excellent / good and adequate into poor so also impacted on the information and evidence we hold in order to take enforcement activity. However, there has been an increase in the notices of proposals to cancel registration and this is due to the drive to ensure consistently poor providers were not able to re-register under the Health and Social Care Act (2008). On 1 October 2009, there were 392 Adult Social Care services that were rated as poor or in enforcement. As of 1 September 2010, 93 of these services have de-registered, 37 of which we were taking enforcement action against. We cancelled the registration of 13 of these but the remaining were voluntary cancellations. 299 of these services are still registered with us. 29 remain poor, 156 are now rated as 1 star, 112 are rated as 2 star and 1 is rated as 3 star. 1 is now rated as ‘new’. It should be noted that these figures may not take into account ‘yoyo’ services i.e. those that are poor, then improve, then decline to poor again, as they may have become poor after 1st October 2009. There are currently 177 poor services in total. This equates to 0.73% of the total number of services. The MI and Performance Reporting Project continues to assess ongoing enforcement reporting requirements as a priority area, the outputs of which will be reflected in future scorecard reports.
Quarter 2 - Spotlight Report 1/2
Regulatory activity: Notifications The National Processing Centre receives notifications from providers which are categorised as either safeguarding concerns, significant issues or routine notifications. These act as triggers for inspection teams to be alerted to concerns about providers and respond proportionately. Notification volumes do not on their own indicate the performance of CQC or the overall quality of care provided by providers. However, the details below indicate the number of occasions on which CQC has been notified of an issue and has monitored response times against targets proportionate to the seriousness of the notification.
Quarter 2 - Spotlight Report 2/2

## ANNEX B refresh
Re-registration of providers | 2010-09-30 | 10 November 2010*
Number of applications received | 10659 | 12822
Number of providers that have received all Notices of Decision | 9922 | 10680
% of providers that have received all Notices of Decision** | 93% | 83%
Total number of Notices of Decision issued | 40043 | 42936
Total number of certificates issued | 0 | 99
Compliance activity | 2010-09-30 | 2010-10-31
Qualitative information uploads to Quality Risk Profiles | 6631 (15 sources) | 7891 (15 sources)
Planned compliance reviews under H&SC Act (year to date): NHS Adult Social Care and Independent Healthcare | 56 N/A | 61 18
Responsive compliance reviews under H&SC Act (year to date): NHS Adult Social Care and Independent Healthcare | 55 N/A | 57 0
NHS providers with conditions (22 in April 2010) | 10 | 10
* due to the timing of drafting this report the data was captured at the latest point possible
** % generated based on measure above 'number of applications received'
Operational activity undertaken since 1 October 2010 Due to the timing of the Quarter 2 Corporate Scorecard Performance Report being presented to Board, this annex includes a refresh of key operational performance measures, to indicate activity levels since 1 October 2010. This shows that a further 2163 providers have submitted registration applications since 30 September, with Notices of Decision and certificates still being processed. NHS compliance activity has continued, but on 1 October we also commenced compliance activity of Adult Social Care and Independent Healthcare providers, with 18 planned reviews undertaken in the first month. Schedules are still being developed which will enable more detailed reporting on compliance activity from Quarter 3. Two reviews have been conducted in November on providers that are on the list of receiving a red QRP alert. Whilst this number may appear low, there is a time delay in identifying concerns and preparing and conducting reviews. Of the 38 NHS providers that received a red alert in the QRP, 34 of these have been identified by regions in their regional risk registers and have reported as major concerns to the Risk and Escalation Committee. Regions review the information in the QRP and ascertain the correct action to take.
Annex B - Data refresh

## Q2 cons old (hidden)
|  | Period Target |  | Last Period |  | This Period |  | July |  | August |  | September |  | Q2 Period
Indicator | Sector | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Directorate | BPM
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
|  | Period Target |  | Last Period |  | Q1 Period |  | July |  | August |  | September |  | Q2 Period |  |  |  | Blank | Blank
Indicator | Sector | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Blank | Blank
[18 empty] | Blank | Blank
1.1.1 Registration of providers | [15 empty] | E |  | Operations | David Lane
Breakdown of % of registrations completed in set time period, by type: Providers | ASC | 474 | 90% |  | 89.2% | 446 | 94.1% | [8 empty] | ­ |  | Operations | David Lane
| IHC | 43 | 90% |  | 75.1% | 72 | 59.7% | [8 empty] | ¯ |  | Operations | David Lane
| NHS | [5 empty] | NA | [10 empty] | Operations | David Lane
Managers | ASC | 1365 | 90% |  | 66.5% | 1177 | 86.2% | [8 empty] | ­ |  | Operations | David Lane
| IHC | 16 | 90% |  | 57.7% | 5 | 31.1% | [8 empty] | ¯ |  | Operations | David Lane
[18 empty] | Blank | Blank
% registrations appealed and upheld | ASC |  |  |  |  | n/a | n/a | [9 empty] | Not yet reportable - expected October 2010. | Operations | David Lane
| IHC |  |  |  |  | n/a | n/a | [9 empty] | Not yet reportable - expected October 2010. | Operations | David Lane
| NHS |  |  |  |  | n/a | n/a | [9 empty] | Not yet reportable - expected October 2010. | Operations | David Lane
Consistency of judgements between regions | [5 empty] | n/a | n/a | [9 empty] | MI requirement - not yet reportable | Operations | David Lane
[18 empty] | Blank | Blank
1.1.2 Manage the re-registering of providers | [17 empty] | Blank | Blank
Breakdown contained within separate Lifecycle report | [17 empty] | Blank | Blank
[18 empty] | Blank | Blank
1.2 Deliver programme to monitor compliance | [17 empty] | Operations | David Lane
Planned compliance reviews completed vs plan under H&SCA | ASC | NA |  |  |  | n/a | n/a | [9 empty] | Activity not yet commenced - October | Operations | David Lane
| IHC | NA |  |  |  | n/a | n/a | [9 empty] | Activity not yet commenced - October | Operations | David Lane
| NHS | 22 | 100% |  |  | 11 | 50% | [10 empty] | Operations | David Lane
Responsive reviews completed vs plan under H&SCA | ASC | NA |  |  |  | n/a | n/a | [9 empty] | Activity not yet commenced | Operations | David Lane
| IHC | NA |  |  |  | n/a | n/a | [9 empty] | Activity not yet commenced | Operations | David Lane
| NHS |  |  |  |  | 23 | [10 empty] | No target for responsive reviews - need to develop reporting against QRP triggers | Operations | David Lane
Conditions reduce over time | NHS |  |  |  |  | 18 | [10 empty] | Proxy measure - reduction to 18 from original 22 at point of registration MI requirement, track trend from September | Operations | David Lane
No. of services subject to enforcement action that return to enforcement within 24 months | ASC |  | 0% |  |  | 4 / 26 | 15% | [9 empty] | Data supplied only covers two regions | Operations | David Lane
| IHC | [5 empty] | No data | [10 empty] | Operations | David Lane
| NHS | [5 empty] | n/a | [10 empty] | Operations | David Lane
% enforcement actions appealed and upheld | ASC |  |  |  |  | No data | 0% | [8 empty] | D | Proxy measure (based on Notices of Proposal to Cancel that proceed past representations) MI requirement, track trend from September | Operations | David Lane
| IHC |  |  |  |  | No data | 13% | [8 empty] | ¯ |  | Operations | David Lane
| NHS | [5 empty] | n/a | [10 empty] | Operations | David Lane
[18 empty] | Blank | Blank
1.3 Assessing the quality of health and social care provision and commissioning (AOQ) | [17 empty] | Blank | Blank
Reviews and Studies - individual project status | [5 empty] | A | [9 empty] | D |  | Regulatory Development | Jacqui Williams
State of Care | [15 empty] | D | Completed in 2009-10 | Regulatory Development | Jacqui Williams
Stroke pathways review | [5 empty] | G | [9 empty] | D | Publication due October | Regulatory Development | Jacqui Williams
Heathcare needs - care homes | [5 empty] | G | [9 empty] | ­ | Publication due December | Regulatory Development | Jacqui Williams
Physical health needs - LD | [5 empty] | R | [9 empty] | D | Review currently postponed - last known position reported | Regulatory Development | Jacqui Williams
Physical health needs - MH | [5 empty] | R | [9 empty] | D | Review currently postponed - last known position reported | Regulatory Development | Jacqui Williams
Social services' response | [5 empty] | G | [9 empty] | ­ | Ops follow up work rescheduled to commence in October, publication due mid-Oct | Regulatory Development | Jacqui Williams
Commissioning for healthy weight | [5 empty] | G | [9 empty] | D | Review currently postponed - last known position reported | Regulatory Development | Jacqui Williams
Support for families with disabled children | [5 empty] | A | [9 empty] | D | Publication due December | Regulatory Development | Jacqui Williams
Impact of financial downturn | [5 empty] | G | [9 empty] | D | Review currently postponed - last known position reported | Regulatory Development | Jacqui Williams
Inspections vs plan (under CSA) | ASC | 4585 | 100% |  | 98.2% | 3724 | 81.2% | [8 empty] | ­ | Reportable only to Sept | Operations | David Lane
| IHC | 51 | 100% |  | 100% | 43 | 84.3% | [8 empty] | ­ | Reportable only to Sept | Operations | David Lane
% provider ratings changes show improvement | 0 Star | [5 empty] | 1% | [8 empty] | ¯ |  | Operations | David Lane
| 1 Star | [5 empty] | 9.1% | [8 empty] | ¯ |  | Operations | David Lane
| 2 Star | [5 empty] | 64.1% | [8 empty] | ­ |  | Operations | David Lane
| 3 Star | [5 empty] | 19.9% | [8 empty] | ¯ |  | Operations | David Lane
| Not yet rated | [5 empty] | 5.8% | [8 empty] | ­ |  | Operations | David Lane
| Rating suspended | [5 empty] | >0.1% | [8 empty] | D |  | Operations | David Lane
[18 empty] | Blank | Blank
1.4 Deliver Mental Health Act / SOAD visiting effectively | [17 empty] | Operations | David Lane
Mental health visits completed vs target |  | 484 | 100% |  |  | 401 | 83% | [8 empty] | ­ |  | Operations | David Lane
Patients seen by SOAD in accordance with their clinical need | [5 empty] | n/a | n/a | [9 empty] | Not reportable - new MI to be defined through MH programme | Operations | David Lane
% Second Opinions completed within set time | Medication | 1040 | 100% |  |  | 488 | 46.9% | [8 empty] | ¯ |  | Operations | David Lane
| ECT | 164 | 100% |  |  | 75 | 45.7% | [8 empty] | ­ |  | Operations | David Lane
| CTO | 215 | 100% |  |  | 64 | 29.7% | [8 empty] | ¯ |  | Operations | David Lane
|  | 1419 |  |  |  | 627 | [11 empty] | Blank | Blank
1.5 Deliver other statutory inspection responsibilities | [17 empty] | Operations | David Lane
% inspections completed vs plan |  |  | 100% |  |  |  | G | [8 empty] | ­ | Consolidates inspection types | Operations | David Lane
| HCAI | 26 |  |  |  | 29 | 111.5% | [8 empty] | ­ | Work required to develop period targets | Operations | David Lane
| Pharmcist |  |  |  |  | 210 | [9 empty] | ­ |  | Operations | David Lane
| IR(ME)R | 3 |  |  |  | 1 | 33% | [8 empty] | ­ |  | Operations | David Lane
| Ofsted | 7 |  |  |  | 7 | 100% | [8 empty] | ­ |  | Operations | David Lane
[18 empty] | Blank | Blank
1.6 Publish information on quality of health and social care services | [17 empty] | Strategic Marketing and Comms | Rebecca Griffith
% key publications on target |  |  | 100% | A | A | A | A | [9 empty] | MI requirement - voting tool on website? | Strategic Marketing and Comms | Rebecca Griffith
Website users say publications and information useful and drive choice |  |  |  | n/a | n/a | n/a | n/a | [9 empty] | MI requirement | Strategic Marketing and Comms | Rebecca Griffith
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
|  | Period Target |  | Last Period |  | Q1 Period |  | July |  | August |  | September |  | Q2 Period |  |  |  | Blank | Blank
Indicator |  | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Blank | Blank
[18 empty] | Blank | Blank
2.1 Effective Shared Services Centre | [15 empty] | E |  | COO Shared Services | Jeremy Parr
Call handling vs target | [6 empty] | G | [8 empty] | ­ |  | COO Shared Services | Jeremy Parr
Safeguarding calls answered within 20 seconds (monthly average) |  | 466 | 90% |  |  | 459 | 96.4% | [8 empty] | ­ | Based on 466 safeguarding calls received, 7 of which were abandoned | COO Shared Services | Jeremy Parr
Registration calls answered within 20 seconds (monthly average) |  | 34249 | 80% |  |  | 33813 | 93.7% | [8 empty] | ­ | Based on 34249 non-safeguarding calls received at the National Contact Centre, 426 of which were abandoned | COO Shared Services | Jeremy Parr
Other calls answered within 20 seconds (monthly average) |  |  | 80% |  |  |  | 90.6% | [8 empty] | ­ |  | COO Shared Services | Jeremy Parr
Caller satisfaction | [5 empty] | n/a | n/a | [9 empty] | MI requirement - not yet reportable | COO Shared Services | Jeremy Parr
Registration processing vs target SC |  | 10 days |  |  |  |  | 8.5 | [8 empty] | ¯ |  | COO Shared Services | Jeremy Parr
HC . |  | 5 days |  |  |  |  | 4 | [8 empty] | D |  | COO Shared Services | Jeremy Parr
[18 empty] | Blank | Blank
2.2 EDHR compliance | [17 empty] | Regulatory Development | Jacqui Williams
Delivery of EDHR strategy on/ off target | [6 empty] | G | [9 empty] | ? % for target | Regulatory Development | Jacqui Williams
Staff diversity profile vs national public sector average | [16 empty] | Proxy measure %s reportable - require national benchmarking | Regulatory Development | Jacqui Williams
Declared staff representation - BME | [5 empty] | 199/1924 | 10.3% | [10 empty] | Regulatory Development | Jacqui Williams
Declared staff representation - Disabled | [5 empty] | 104/1924 | 5.4% | [10 empty] | Regulatory Development | Jacqui Williams
Declared staff representation - LGBT sexual orientation | [5 empty] | 46/1924 | 2.4% | [10 empty] | Regulatory Development | Jacqui Williams
2.3 Communications | [17 empty] | Strategic Marketing and Comms | Rebecca Griffith
Website usage statistics | [6 empty] | G | [9 empty] | Benchmarking data or internal targets required to provide context for future reporting | Strategic Marketing and Comms | Rebecca Griffith
Visits to the website |  | n/a |  |  |  | 1351722 | [9 empty] | ­ |  | Strategic Marketing and Comms | Rebecca Griffith
Unique visitors to the website |  | n/a |  |  |  | 596299 | [9 empty] | ­ |  | Strategic Marketing and Comms | Rebecca Griffith
Average length of visit |  | n/a |  |  |  | 7:43 mins | [9 empty] | ¯ |  | Strategic Marketing and Comms | Rebecca Griffith
Inspection reports - number downloaded |  | n/a |  |  |  | 620690 | [9 empty] | ­ |  | Strategic Marketing and Comms | Rebecca Griffith
Newsletter subscribers (running total) |  | n/a |  |  |  | 43943 | [9 empty] | ¯ |  | Strategic Marketing and Comms | Rebecca Griffith
Website users say information was useful | [5 empty] | n/a | n/a | [9 empty] | MI requirement - voting tool on website? | Strategic Marketing and Comms | Rebecca Griffith
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
|  | Period Target |  | Last Period |  | Q1 Period |  | July |  | August |  | September |  | Q2 Period |  |  |  | Blank | Blank
Indicator |  | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Blank | Blank
[18 empty] | Blank | Blank
3.1 Workforce is skilled | [15 empty] | E |  | Human Resources | Michelle Fox
Average no. learning and development days per staff member | [5 empty] | n/a | n/a | [9 empty] | MI requirement | Human Resources | Michelle Fox
Staff performance improvement measure | [5 empty] | n/a | n/a | [9 empty] | MI requirement to track development through PDR process | Human Resources | Michelle Fox
[18 empty] | Blank | Blank
3.2 Workforce is engaged | [17 empty] | Human Resources | Michelle Fox
% staff with objectives set | [5 empty] | n/a | n/a | [9 empty] | MI requirement to track progress through PDR process | Human Resources | Michelle Fox
Culture change on target/ off target | [6 empty] | A | [9 empty] | Supporting detail to be developed in line with top level measures | Human Resources | Michelle Fox
[18 empty] | Blank | Blank
3.3 Workforce has good working environment | [17 empty] | Human Resources | Michelle Fox
Progress of staff survey action plan |  |  | 100% |  |  | n/a | n/a | [9 empty] | MI requirement | Human Resources | Michelle Fox
Successful grievances |  |  | <10% |  |  | n/a | n/a | [9 empty] | MI requirement | Human Resources | Michelle Fox
HR indicators | [16 empty] | Indicators to be developed further, data taken from existing HR directorate reporting | Human Resources | Michelle Fox
• Successful payroll run |  |  | 100% |  |  |  | 100% | [10 empty] | Human Resources | Michelle Fox
• Headcount | [5 empty] | 1928 | [10 empty] | Average across the quarter, reduction of 4 posts overall compared to 2009-10 Q4 | Human Resources | Michelle Fox
• Turnover | [5 empty] | -48 | [10 empty] | Turnover rate calculation in development, 56 leavers across the quarter compared to an average headcount of 1928 | Human Resources | Michelle Fox
• Temporary staff breakdown | [5 empty] | 239 | [10 empty] | Figure represents the end of June position, not an average across the quarter, compares to FTE headcount of 1928 | Human Resources | Michelle Fox
• Absence data | [5 empty] | See note | 2.58% | [9 empty] | 4224.44 FTE days sickness of 163,827.99 FTE days workable (2.58) | Human Resources | Michelle Fox
• Time taken to recruit | [5 empty] | n/a | n/a | [8 empty] | D | It is anticipated that data will not be available until August. | Human Resources | Michelle Fox
[18 empty] | Blank | Blank
3.4 Deliver high quality service to our customers | [17 empty] | Governance and Legal Services | Jenny Wright
Stakeholder feedback on customer facing services | [5 empty] | n/a | n/a | [9 empty] | MI requirement - regular SH feedback for all customer facing services | Strategic Marketing and Comms | Rebecca Griffith
Patient postcards indicate good MH service | [5 empty] | 83 | 100% | [9 empty] | Proxy measure re MH. MI requirement - regular SH feedback for all customer facing services | Operations | David Lane
Corporate complaints upheld |  |  | <10% |  |  | n/a | n/a | [9 empty] | MI requirement for outcomes of complaints | Governance and Legal Services | Jenny Wright
Stage 1 requests received | [5 empty] | 27 | [9 empty] | ­ | Proxy measures - indication of regional complaints received and escalated | Governance and Legal Services | Jenny Wright
Stage 2 requests received | [5 empty] | 14 | [9 empty] | ­ |  | Governance and Legal Services | Jenny Wright
Stage 2 reviews carried over from previous month | [5 empty] | 9 | [11 empty] | Governance and Legal Services | Jenny Wright
Number of complaints taken to external investigation | [5 empty] | 1 | [9 empty] | D |  | Governance and Legal Services | Jenny Wright
Requests for internal review (complaints against FOI and DPA decisions) | [5 empty] | 7 | [9 empty] | ­ | See Annex 4.3 | Governance and Legal Services | Jenny Wright
Customer services strategy implementation - project progress |  |  | 100% |  |  | n/a | n/a | [9 empty] | MI requirement as a deliverable of project | Strategic Marketing and Comms | Rebecca Griffith
[18 empty] | Blank | Blank
3.5 Engaging effectively with stakeholders | [17 empty] | Strategic Marketing and Comms | Rebecca Griffith
High profile public consultations responded to | [5 empty] | n/a | n/a | [9 empty] | MI requirement. Supporting detail to be developed in line with top level measures. | Strategic Marketing and Comms | Rebecca Griffith
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
|  | Period Target |  | Last Period |  | Q1 Period |  | July |  | August |  | September |  | Q2 Period |  |  |  | Blank | Blank
Indicator |  | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Blank | Blank
[18 empty] | Blank | Blank
4.1 Income/ expenditure is controlled and planned |  | Budget | Expenditure | Variance | Budget | Expenditure | Variance | [6 empty] | Expenditure | Variance | E |  | Finance & Corporate Services | Kirsty McTaggart
On/ off target within, revenue, transition, capital |  |  |  |  | A | [11 empty] | Annual Budget cash envelope for recurring revenue = £82.1m, Transition budget = £17.5m; Capital budget = £19.6m. | Finance & Corporate Services | Kirsty McTaggart
Recurring revenue position - YTD |  | £21.6m |  |  | £21.6m | £17.4m | £4.2m | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
Transition position - YTD |  | £6.6m |  |  | £6.5m | £3.0m | £3.6m | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
Capital position - YTD |  |  |  |  | n/a | £2.6m | n/a | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
Cost of finance function as a % of the business |  |  | 1.5% |  |  | - | 1.3% | [9 empty] | Internal target 1.5%. Average finance function cost across H&SC ALBs is 4.6% | Finance & Corporate Services | Kirsty McTaggart
[18 empty] | Blank | Blank
4.2 Develop IS and ICT | [17 empty] | Finance & Corporate Services | Kirsty McTaggart
[17 empty] | Supporting detail to be developed across key IS & ICT services | Finance & Corporate Services | Kirsty McTaggart
IT Service - on/off target | [6 empty] | G | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
% ICT service incidents closed within target |  |  | 99% |  |  |  | 99.6% | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
% helpdesk responses rated excellent | [6 empty] | 64.9% | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
% helpdesk responses rated poor | [6 empty] | 6.4% | [10 empty] | Finance & Corporate Services | Kirsty McTaggart
Cost of IT service as a % of the business |  |  | 5.1% |  |  |  | 13.5% | [9 empty] | Internal target TBC - average IT function cost across H&SC ALBs is 5.1% | Finance & Corporate Services | Kirsty McTaggart
4.3 Deliver high standard of corporate governance | [17 empty] | Governance and Legal Services | Jenny Wright
Information requests closed within target time |  | 234 | 100% |  |  | 221 | 94.4% | [9 empty] | Consolidates DPA & FOI - breakdown required in future reporting. Expand to include PQs and requests from other public bodies. | Governance and Legal Services | Jenny Wright
FOI | [5 empty] | n/a | n/a | [10 empty] | Governance and Legal Services | Jenny Wright
DPA | [5 empty] | n/a | n/a | [10 empty] | Governance and Legal Services | Jenny Wright
PQ | [5 empty] | n/a | n/a | [10 empty] | Governance and Legal Services | Jenny Wright
Requests for internal review (complaints against FOI and DPA decisions) |  | 0 |  |  |  | 7 | [11 empty] | Governance and Legal Services | Jenny Wright
Serious Untoward Incidents reported to the Information Commissioner's Office (information handling) |  | 0 |  |  |  | 2 | [11 empty] | Governance and Legal Services | Jenny Wright
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
[18 empty] | Blank | Blank
|  | Period Target |  | Last Period |  | Q1 Period |  | July |  | August |  | September |  | Q2 Period |  |  |  | Blank | Blank
Indicator |  | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Trend | Comments | Blank | Blank
[18 empty] | Blank | Blank
5.1 Deliver Registration Programme | [14 empty] | (RAG) | E |  | Regulatory Development | Jacqui Williams
Programme progress - % milestones achieved |  |  | 100% |  |  |  | A/R | [8 empty] | D | Milestones not reported for Q1 | Regulatory Development | Jacqui Williams
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Regulatory Development | Jacqui Williams
5.2 Deliver Assessments of Quality Programme | [17 empty] | Regulatory Development | Jacqui Williams
Programme progress - % milestones achieved |  |  | 100% |  |  |  | A | [8 empty] | D | Milestones not reported for Q1 | Regulatory Development | Jacqui Williams
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Regulatory Development | Jacqui Williams
5.3.1 Deliver Field Force Model Implementation Programme | [17 empty] | Chief Operating Officer | Alun Jones
Programme progress - % milestones achieved |  |  | 100% |  |  |  | G | [8 empty] | D | Milestones not reported for Q1 | Chief Operating Officer | Alun Jones
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Chief Operating Officer | Alun Jones
5.3.2 Deliver HQ Review Programme | [17 empty] | Chief Operating Officer | Alun Jones
Programme progress - % milestones achieved |  |  | 100% |  |  |  | ? | [8 empty] | D | Milestones not reported for Q1, being scoped | Chief Operating Officer | Alun Jones
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Chief Operating Officer | Alun Jones
5.4 Deliver Shared Service Transformation Programme | [17 empty] | COO Shared Services | Jeremy Parr
Programme progress - % milestones achieved |  |  | 100% |  |  |  | A | [8 empty] | D | Milestones not reported for Q1 | COO Shared Services | Jeremy Parr
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | COO Shared Services | Jeremy Parr
5.5 Deliver Modernising Mental Health Act Programme | [17 empty] | Chief Operating Officer | Alun Jones
Programme progress - % milestones achieved |  |  | 100% |  |  |  | A | [8 empty] | D | Milestones not reported for Q1 | Chief Operating Officer | Alun Jones
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Chief Operating Officer | Alun Jones
5.6 Deliver People's Voices Programme | [17 empty] | Strategic Marketing and Comms | Rebecca Griffith
Programme progress - % milestones achieved |  |  | 100% |  |  |  | A | [8 empty] | D | Milestones not reported for Q1 | Strategic Marketing and Comms | Rebecca Griffith
% benefits realised |  |  | 100% | [13 empty] | MI requirement linked to portfolio development | Strategic Marketing and Comms | Rebecca Griffith
1. Regulatory Activity - Supporting Detail
2. Supporting Activities - Supporting Detail
3. Stakeholders - Supporting Detail
1. Regulatory Activity
4. Financial and other resources - Supporting Detail
5. Change - Supporting Detail
Corporate Performance Report for period - Quarter 2
Financial and other resources performance highlights / RAG summary / Narrative Summary As with previous data requests please submit: - supporting statement for RAG ratings where appropriate. - narrative summary to clarify positio or support data where appropriate. Please also identify any Issues (& outlining mitigating actions to the issues) on any of the above sections as appropriatte. (Please identify section by it's sub section number i.e. 1.5). ●

## Data (hidden)
Directorates | BPM
Chief Operating Officer | Alun Jones
COO Shared Services | Jeremy Parr
Finance & Corporate Services | Kirsty McTaggart
Governance and Legal Services | Jenny Wright
Human Resources | Michelle Fox
Intelligence | Sarah Greig
Operations | David Lane
Operations 2 | Felix Rullhusen
Regulatory Development | Jacqui Williams
Strategic Marketing and Comms | Rebecca Griffith
Blank | Blank
COO Business transformation | Alun Jones
Regulatory Development EDHR/ Involvement | Jacqui Williams