## 0.Instructions and Summary info
Project and customer details
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Revisionlist
Version | Comment | Edited by
1 | draft | JMA01
1.2 | updates | JMA01
1.3 | updated scope | JMA01
1.4 | generalization | JMA01
Instructions and guidelines
1. Fill in the project and customer details on this worksheet (0.Instructions and Summary info) 2. Use either the activity/deliverable based estimations on sheet 1A OR the use case based estimations on 1B (use case based gives a rougher estimate for early stage estimations) 3. Use the resource planning sheet 2 to see how much time you need and for how many weeks, you will also have to see how many hours you need from different kind of resources (e.g. PM, Off-shore, Tech spec., senior consultant, consultant). Remember that NO resource can register all their working hours to a project every week (that is just realistic in shorter periods of time)! Some activities do also take a longer calendar time than it takes man time (e.g. printshop configuration). Use this sheet to get an overall estimation on how realistic the time plan is. Do you need to keep some resources in the project to have them updated and make sure that they can plan for activities later on in the project - or to be available after go live etc to ensure that the first live runs are correct? Capture this in the resource planning! 4. Make sure that the estimations in 1A OR 1B are the same as in the resource planning sheet! (adjust one or the other to achieve this!) 5. Use the sheet "3. Validation of plan" to self-check the quality of your plan! 6. When the project is running, you can make copies for e.g. every week of your plan (this spreadsheet) and also use the "4. Resource tracking (actual)" to register time to your project for follow up purposes.

## 1A. Activity based est
Project and Task Planning
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Phases and Tasks
Initiation | Min | Avg. | Max | Expected | Project Role
Current Process Overview | 0.5 | 0.5 | 2 | 0.75 | PM
Solution Architecture | 0.5 | 0.5 | 2 | 0.75 | PM
Project Organisation | 0.25 | 0.25 | 0.5 | 0.29167 | PM
Decision Making Framework | 0.25 | 0.25 | 0.5 | 0.29167 | PM
Other … |  |  |  | 0
Other … |  |  |  | 0
Project Planning | 1 | 1 | 2 | 1.1667 | PM
Sum of Initiation Activities | 2.5 | 2.5 | 7 | 3.25
Definition | Min | Avg. | Max | Expected
Requirement Specification Gathering | 1 | 1 | 3 | 1.3333 | Consultant
Test Plan | 1 | 1 | 3 | 1.3333 | PM
Requirements Sign-off Meeting | 0.25 | 0.25 | 0.25 | 0.25 | PM
Other … |  |  |  | 0
Other … |  |  |  | 0
Project Plan Update | 0.25 | 0.25 | 0.25 | 0.25 | PM
Sum of Definition Activities | 2.5 | 2.5 | 6.5 | 3.1667
Realization | Min | Avg. | Max | Expected
Installation |  |  |  | 0
TEST install: StreamServer, Framework & Control Center, Design Center & Collector | 3 | 3 | 4 | 3.1667 | Consultant
PROD install: StreamServer, Framework & Control Center, Design Center & Collector (2 servers, shared db) | 3 | 3 | 4 | 3.1667 | Consultant
DR install: StreamServer, Framework & Control Center, Design Center & Collector (2 servers, shared db) | 3 | 3 | 4 | 3.1667 | Consultant
Layout Development
Message 1 | 1 | 2 | 3 | 2 | Consultant
Message 2 | 1 | 2 | 3 | 2 | Consultant
Message 3 | 1 | 2 | 3 | 2 | Consultant
Message 4 | 1 | 1 | 2 | 1.1667 | Consultant
Message 5 | 2 | 3 | 5 | 3.1667 | Consultant
Collector Config. | 1 | 1 | 2 | 1.1667 | Consultant
Post Processing
OMR | 1 | 2 | 3 | 2 | Consultant
Enveloping | 1 | 2 | 3 | 2 | Consultant
Labels | 1 | 1 | 3 | 1.3333 | Consultant
Sheet Layout | 1 | 1 | 3 | 1.3333 | Consultant
Platform Configuration |  |  |  | 0
Platform Configuration (device integration) | 1 | 1 | 2 | 1.1667
Platform Configuration 2 ... |  |  |  | 0
Platform Configuration 3 ... |  |  |  | 0 | Consultant
Sum of Realization Activities | 21 | 27 | 44 | 28.8333
Testing | Min | Avg. | Max | Expected
Test Support and Test Approval | 5 | 7 | 15 | 8 | Consultant
Follow up and re-work | 2 | 3 | 5 | 3.1667 | Consultant
UAT Support | 1 | 1 | 2 | 1.1667 | Consultant
Other … |  |  |  | 0
Other … |  |  |  | 0
Sign-off Tested Solution Meeting | 0.25 | 0.25 | 0.25 | 0.25 | PM
Sum of Testing Activities | 8.25 | 11.25 | 22.25 | 12.5833
Go Live | Min | Avg. | Max | Expected
Final and complete documentation |  | 16 | 4 | 11.3333 | Consultant
Customer knowledge transfer and education |  |  |  | 0 | Consultant
Delivery to live environment |  |  |  | 0 | Consultant
Project Sign Off Meeting | 0.25 | 0.25 | 0.25 | 0.25 | PM
Sum of Go Live Activities | 0.25 | 0.25 | 0.25 | 11.5833
| Min | Avg. | Max
Total Sum Activities | 34.5 | 43.5 | 80 | 59.4167 | All
Management and Administration
% To add on Estimated Activities: | Min | Avg. | Max | Expected
20% | 6.9 | 8.7 | 16 | 11.2333 | PM
^ Enter the appropriate managment and administration overhead-percentage above!
| Min | Avg. | Max | Expected
Project Total | 41.4 | 52.2 | 96 | 70.65
Optional Activities | Min | Avg. | Max | Expected
Final and complete documentation | 2 | 3 | 3 | 2.8333 | Consultant
TEST install: Composition Center | 1 | 1 | 2 | 1.1667 | Consultant
PROD install: Composition Center | 1 | 1 | 2 | 1.1667 | Consultant
DR install: Composition Center | 1 | 1 | 2 | 1.1667 | Consultant
Composition Center config. | 2 | 3 | 4 | 3 | Consultant
Handover Workshop | 1 | 1 | 1 | 1 | PM
| 8 | 10 | 14 | 10.3333
| Min | Avg. | Max
Project Total incl. Optional Activities | 49.4 | 62.2 | 110 | 80.9833
This is a task planning sheet that uses a min/avg/max-model for calculation of expected time needed for a project.
The model is simple (6-sigma) and calculates an expected time for each task with the following formula expected time = (max + min + 4*avg)/6
Enter tasks for each phase in the StreamServe Methodology and then enter min, avg and max.
min= when things go smooth, max = when they don't, avg = your expected average time for the task
Each tasks expected duration is calculated in the gray cells, sums are made in yellow cells. All blue text indicates that it should be removed/replaced.
Make sure you enter min,avg and max on eaxh row - or the formula will not work!

## 1B. Use case based est.
Project and task planning
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Use case time multiple: | 40 | (This is a time multiple used to estimate the project, set it to a number you think is appropriate - it depends on the average size of your use cases)
Instructions
A Use-case is a functional/logical aspect of the solution. That means that is not technical - it is rather the perspective of the user. E.g. "Print invoice", "Print Collective Invoice" or "Change marketing message for correspondence letters", "Send e-invoice", "View bills to customer when recieveing call center call" etc etc. Every use case describes a process with value to the end user. The use case does not describe technical things like "installation StreamServe". To use this planning template you must possess very good skills in understanding the needs of a customer and to express the functionality of a solution with the customers words. You must also have good PM skills since you will need to take into account planning, specifications, meetings, mgmt overhead, installation, configuration etc etc on every row of the time estimation WITHOUT spellingt it out (everything is included in this estimation).
1=LOW, 2=MEDIUM, 3=HIGH (you may use more levels if needed)
Use case name/number | Level of complexity | Comment
Send welcome letter | 1
View invoices | 2
Send e-invoice to sub contractors | 1
(examples use case) | 2
(example use case) | 3
Sum: | 360 | (this is the time for the whole project)

## 1B. Use case based est (hidden)
Project and task planning
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Use case time multiple: | 40 | (This is a time multiple used to estimate the project, set it to a number you think is appropriate - it depends on the average size of your use cases)
Instructions
A Use-case is a functional/logical aspect of the solution. That means that is not technical - it is rather the perspective of the user. E.g. "Print invoice", "Print Collective Invoice" or "Change marketing message for correspondence letters", "Send e-invoice", "View bills to customer when recieveing call center call" etc etc. Every use case describes a process with value to the end user. The use case does not describe technical things like "installation StreamServe". To use this planning template you must possess very good skills in understanding the needs of a customer and to express the functionality of a solution with the customers words. You must also have good PM skills since you will need to take into account planning, specifications, meetings, mgmt overhead, installation, configuration etc etc on every row of the time estimation WITHOUT spellingt it out (everything is included in this estimation).
1=LOW, 2=MEDIUM, 3=HIGH (you may use more levels if needed)
Use case name/number | Level of complexity | Comment
Send welcome letter | 1
View invoices | 2
Send e-invoice to sub contractors | 1
(examples use case) | 2
(example use case) | 3
Sum: | 360 | (this is the time for the whole project)

## 2. Resource planning
Resource planning
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Planned time (days)
Month |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  |  | Month 6
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | Sum (days)
Resource:
Resource 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 54
Resource 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 81
Project Manager Resource |  | Month 5 19: 1; Month 5 20: 1; Month 5 21: 1; Month 5 22: 2; Month 6 23: 1; Month 6 24: 2; Month 6 25: 1; Month 6 26: 2; Month 6 27: 2 | 13
StreamServe Offshore |  | Month 5 19: 2; Month 5 20: 2; Month 5 21: 2; Month 5 22: 2; Month 6 23: 2; Month 6 24: 2; Month 6 25: 2; Month 6 26: 2; Month 6 27: 2 | 18
other | [28 empty] | 0
other | [28 empty] | 0
Planned used time |  | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 98 | 106 | 114 | 123 | 131 | 140 | 148 | 157 | 166 | 166
Totalt remaining planned |  | 161 | 156 | 151 | 146 | 141 | 136 | 131 | 126 | 121 | 116 | 111 | 106 | 101 | 96 | 91 | 86 | 81 | 76 | 68 | 60 | 52 | 43 | 35 | 26 | 18 | 9 | 0
This is an example of a simple resource planning sheet. Edit with your appropriate weeks and then you vill have a good overview of the planned time of your project.
Use the next sheet of this workbook to enter actual time used for each week, this will make it easy to track planned time / actual time per week.

## 3. Validation of plan
Project plan quality self-check
Customer: | Customer Name
Project: | Project Name
Date: | Date
Author: | Author
Please indicate with Y/N (Yes/No) for each question! A high number of Yes indicates that your plan have a higher quality.
Question | Answer | Comments
Is management and meeting overhead included in estimate? (20% for standard project, 30% for a offshore project or fixed price project)
Are time for workshop meetings around design and requirements included in estimate?
Is time for component testing included? (total testing is typically equal to implemenation time but customers often do the testing so we need to plan for component testing and support for testing)
Is go-live support included in estimate? (it is wise to have resources stand by for first production as well)
Does the estimate cover all needed documentation?
Have you had the planning reviewed by a colleague?
Have you made sure "any" resource can deliver according to estimate? (project start is nearly always delayed so it is best to not take into account that a specific resources will be available)
Is the estimate depending on deliverables from outside of project? How is estimate taking delay of those deliverables into account? (e.g. Printshop configuration typically takes some calendar time)
Is support for the configuration of production environment included?
Are time for workshop meetings around design and requirements included in estimate?
Are time for requirement walk trough and reading included for every resource?
Are installation and configuration for every needed environment included (local,dev, test, acc, prod etc.)

## 4. Resource tracking (actual)
Resources tracking YYYY
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  |  | Month 6
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | Sum (days)
Resources
Resource 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 54
Resource 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 81
Project Manager Resource |  | Month 5 19: 1; Month 5 20: 1; Month 5 21: 1; Month 5 22: 2; Month 6 23: 1; Month 6 24: 2; Month 6 25: 1; Month 6 26: 2; Month 6 27: 2 | 13
StreamServe Offshore |  | Month 5 19: 2; Month 5 20: 2; Month 5 21: 2; Month 5 22: 2; Month 6 23: 2; Month 6 24: 2; Month 6 25: 2; Month 6 26: 2; Month 6 27: 2 | 18
Trainer |  | Month 4 14: 5; Month 4 15: 5
other
Actual time used |  | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 75 | 85 | 90 | 95 | 100 | 108 | 116 | 124 | 133 | 141 | 150 | 158 | 167 | 176
This sheet is used to track the resource usage. Enter resource usage each week and then you will have a simple view of how much time that is actually spent in your project.
(Use the same weeks as you used in your Resource planning)
Total planned: | 166
(from Resource Planning sheet)