## RACI Chart 01 Example
RACI CHART
Process Name / Description: ___________________________________________________________________________________________________
Created On: __________________________________________________________________________________________________________________
Created by: _________________________________________________________________________________________________________________+A1_
Attributes | Facilities Mgr | Plant Mgr | HR | Security | Project Mgr
Identify a minimum of three asphalt contractors from Angie's List | C | - | - | - | R
Arrange for contractor visits and quotes | I | - | - | - | R
Review quotes and references, make contractor selection | A | I | I | - | R
Review and finalize contract, lock in plant shutdown week | I | I | - | - | R
Communicate project to shutdown maintenance crew, make sure all vehicles are removed from the lot | I | I | R | I | I
Provide security gate access codes for asphalt crew by June 15 | I | - | A | R | I
Oversee the project during the plant shutdown week, ensure it is completed on time | A | I | I | - | R