## Residential Construction
RESIDENTIAL CONSTRUCTION SCHEDULE
Task No. | Task Name | Start Date | End Date | Actual Completion Date | Variance (In Days) | Resource | Remarks
56 | Blow-In insulation | 2020-07-05 | 2020-07-06 | 2020-07-06 | 0 | Installation Team
57 | Drywall nailing inspection | 2020-07-07 | 2020-07-07 | 2020-07-08 | -1 | Quality Control Team | Delay in inspection notification
58 | Order finish package | 2020-07-07 | 2020-07-07 | 2020-07-07 | 0 | Purchasing Team
59 | Tape and texture drywall | 2020-07-07 | 2020-07-14 | 2020-07-13 | 1 | Installation Team
60 | Deliver finish package | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | Supplier
61 | Finish carpentry | 2020-07-15 | 2020-07-20 | 2020-07-20 | 0 | Carpentry Team
62 | Painting | 2020-07-20 | 2020-07-25 | 2020-07-25 | 0 | Painting Team
63 | Phase 4 Exterior Finish | 2020-06-21 | 2020-07-19 | 2020-07-19 | 0
64 | Install house wrap | 2020-06-21 | 2020-05-22 | 2020-05-27 | -5 | Installation Team | Material not available on site
65 | Roofing | 2020-06-22 | 2020-06-27 | 2020-06-23 | 4 | Installation Team
66 | Masonry | 2020-06-22 | 2020-06-29 | 2020-06-29 | 0 | Masonry Team
67 | Siding / Stucco | 2020-06-29 | 2020-07-05 | 2020-07-05 | 0 | Installation Team
68 | Concrete prefinal grade | 2020-07-05 | 2020-06-30 | 2020-06-27 | 3 | Masonry Team
69 | Soffit & fascia | 2020-07-05 | 2020-07-07 | 2020-07-07 | 0 | Installation Team
70 | Pour driveway and walk | 2020-07-06 | 2020-07-08 | 2020-07-05 | 3 | Masonry Team
71 | Foundation purging | 2020-07-08 | 2020-07-11 | 2020-07-11 | 0 | Masonry Team
72 | Exterior painting | 2020-07-11 | 2020-07-12 | 2020-07-12 | 0 | Painting Team
73 | Landscaping | 2020-07-12 | 2020-07-19 | 2020-07-23 | -4 | Landscaping Team | Issue encountered with plant supplier
74 | Phase 5 Interior Finish | 2020-07-25 | 2020-08-05 |  | -783
75 | Order appliances | 2020-07-25 | 2020-07-25 | 2020-07-25 | 0 | Purchasing Team
76 | Tub & shower wall finish | 2020-07-25 | 2020-07-28 |  | -791 | Installation Team
77 | Install resilient/hard floors | 2020-07-28 | 2020-08-02 |  | -786 | Installation Team
78 | Install cabinets & countertops | 2020-08-02 | 2020-08-03 |  | -785 | Installation Team
79 | Deliver appliances | 2020-08-02 | 2020-08-02 |  | -786 | Supplier
80 | Carpentry pick-up | 2020-08-03 | 2020-08-04 |  | -784 | Carpentry Team
81 | Install appliances | 2020-08-03 | 2020-08-04 |  | -784 | Installation Team
82 | Finish electrical | 2020-08-03 | 2020-08-04 |  | -784 | Electrical Team
83 | Install cabinets & countertops | 2020-08-02 | 2020-08-03 |  | -785 | Installation Team
84 | Deliver appliances | 2020-08-02 | 2020-08-02 |  | -786 | Supplier
85 | Carpentry pick-up | 2020-08-03 | 2020-08-04 |  | -784 | Carpentry Team
86 | Install appliances | 2020-08-03 | 2020-08-04 |  | -784 | Installation Team
87 | Finish electrical | 2020-08-03 | 2020-08-04 |  | -784 | Electrical Team
88 | Install appliances | 2020-08-03 | 2020-08-04 |  | -784 | Installation Team
89 | Finish electrical | 2020-08-03 | 2020-08-04 |  | -784 | Electrical Team
Formulas:
Variance (In Days) = IF([Actual Completion Date]="",[End Date]-TODAY(),[End Date]-[Actual Completion Date])