## Sample Project Schedule
PROJECT SCHEDULE
PROJECT NAME |  |  |  | START DATE
Positive Charge EMV Station Installations |  |  |  | 2025-05-05
PROJECT MANAGER |  |  |  | END DATE
Jane Matthews |  |  |  | 2026-02-10
PROJECT PHASES | TIMELINE |  |  | PROJECT NOTES
| START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
CONCEPTION AND INITIATION | 2025-05-05 | 2025-08-10 | 95
Project Charter | 2025-05-05 | 2025-07-01 | 58 | Defined/Driven by Project Management |  | Operations and Sales Engineers
Project Initiation | 2025-05-10 | 2025-08-10 | 93
DEFINITION AND PLANNING | 2025-06-10 | 2026-03-01 | 265
Scope and Budget | 2025-06-22 | 2025-08-04 | 44 |  | 2,345,123.00 for all 126 EV location installations |  | Going over budget could risk installations in the SW
Work Breakdown Schedule (WBS) | 2025-07-14 | 2025-11-01 | 111
Communication Plan | 2025-07-14 | 2026-01-20 | 191 | Defined/Driven by Marketing
Risk Management | 2025-08-01 | 2025-10-01 | 62
LAUNCH / EXECUTION | 2025-08-14 | 2025-08-30 | 17
Status and Tracking | 2025-09-01 | 2025-12-10 | 101
Key Performance Indicators (KPIs) | 2025-10-01 | 2025-11-15 | 46
Quality | 2025-10-01 | 2025-12-01 | 62
Forecasts | 2025-11-01 | 2025-12-01 | 31
PERFORMANCE AND CONTROL | 2025-11-10 | 2026-12-10 | 396
Objectives | 2025-12-01 | 2026-02-10 | 72
Quality Deliverables | 2026-02-01 | 2026-02-28 | 28
Effort and Cost Tracking | 2026-03-01 | 2026-03-30 | 30
Performance | 2026-04-01 | 2026-04-30 | 30
PROJECT CLOSE | 2026-05-01 | 2026-05-21 | 21
Post mortem | 2026-05-01 | 2026-05-08 | 7
Project punchlist | 2026-05-08 | 2026-05-15 | 7
Reporting | 2026-05-15 | 2026-05-21 | 7