## Phase II workplan draft
Project WORK PLAN Template in Excel
Company Name or LOGO | [5 empty] | Add note and instructions here
Meetings
Work in process
|  | Check-ins/meetings with Bridgespan | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
| X | Major deadlines/deliverables | Insert Dates | [18 empty] | Insert Dates
|  |  | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15
| Meetings | Working Group Meetings | bar: Insert Dates 9; Insert Dates 16; Insert Dates 23; Insert Dates 30; Insert Dates 6; Insert Dates 13
Working Group 1on1 meetings with Project Coordinator | bar: Insert Dates 9; Insert Dates 15; Insert Dates 22; Insert Dates 29; Insert Dates 5; Insert Dates 12
Project Coordinator Check-ins with Bridgespan | bar: Insert Dates 11; Insert Dates 18; Insert Dates 25; Insert Dates 1; Insert Dates 8; Insert Dates 15
2.2A Economic Analysis
<Insert team lead>
Determine break-out/segmentation of programs | bar: Insert Dates 7 to Insert Dates 9
Determine 12 month timeframe to use in analysis | bar: Insert Dates 7 to Insert Dates 9
Collect financial reporting required to populate analysis | bar: Insert Dates 7 to Insert Dates 11
Share draft workplan, program break-out and timeframe with Bridgespan | bar: Insert Dates 9
Discuss with Bridgespan, get feedback | bar: Insert Dates 11
Conduct staff allocation exercise | bar: Insert Dates 14 to Insert Dates 22
Input all available data into model - identify gaps requiring additional data gathering | bar: Insert Dates 22 to Insert Dates 25
Conduct, complete additional data gathering, review for accuracy with working group | bar: Insert Dates 22 to Insert Dates 25
Send to Bridgespan to review | bar: Insert Dates 25
Discuss with Bridgespan, get feedback | bar: Insert Dates 1
Make revisions, conduct final 'validation check, and begin to share with working team | bar: Insert Dates 4 to Insert Dates 15
2.2B Program Analysis
<Insert team lead>
Determine break-out/segmentation of programs | bar: Insert Dates 7 to Insert Dates 9
Assign roles/responsibilities for assessment of each program | bar: Insert Dates 7 to Insert Dates 9
Determine time-period for which data will be collected (if available) | bar: Insert Dates 7 to Insert Dates 9
Share draft workplan for this workstream to Bridgespan | bar: Insert Dates 9
Discuss with Bridgespan, get feedback | bar: Insert Dates 11
Identify target data, and what is easily available on participants, performance by program | bar: Insert Dates 14 to Insert Dates 18
Determine metrics to use in assessing program operations | bar: Insert Dates 14 to Insert Dates 18
Share target metrics, data gathering targets with Bridgespan | bar: Insert Dates 18
Discuss with Bridgespan, get feedback
Collect data on participants and performance by program | bar: Insert Dates 22 to Insert Dates 1
Collect data on program performance against metrics | bar: Insert Dates 22 to Insert Dates 1
Periodic check-ins, feedback of learnings with working group | bar: Insert Dates 30; Insert Dates 6
Synthesize key observations, identification of differences between target and actual in program execution, participants, performance | bar: Insert Dates 4 to Insert Dates 15
Share with Bridgespan for review, feedback | bar: Insert Dates 14
[Insert additional analyses]
3) |  | Knowledge capture
| a) | Kick-off
Schedule knowledge meetings
Send case profile firm to Nicolle
Send client and case intro email to the firm
Check with Alex for key points to emphasize
Prepare materials for kick-off meeting with K team | bar: Insert Dates 7
Refine and circulate Learning Agenda and Resource List | bar: Insert Dates 7 to Insert Dates 8
| b) | Case-in-progress
Revisit Learning Agenda (mid-case)
| c) | Wrap-up
Create WP for case-end K capture - AC input re: WP milestones
Prepare materials for case-end meeting
Prepare memo sections
Draft/ integrate memo sections and submit draft to Alex
(Alex to review memo and provide feedback)
Finalize memo
| d) | Case-end
Compile key files to post on BRIDGE (refine/disguise/collect files)
Archive key materials (w/team)
Submit final memo to K team