## Project Plan and Gantt
WORK PLAN
Project Name | Product Release
Project Manager | Alex B.
Project Deliverable
Scope Statement:
Start Date | 2015-09-02
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-03 | 1 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-12 | 5 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-16 | 2015-09-17 | 1 | In progress
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
DB Development | Shari W. | 2015-09-22 | 2015-09-24 | 2 | Not started
API Development | Shari W. | 2015-09-23 | 2015-09-27 | 4 | Not started
UI Client | Alex B. | 2015-09-25 | 2015-09-29 | 4 | Not started
Testing | Kennedy K. | 2015-09-24 | 2015-10-02 | 8 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-06 | 2015-10-09 | 3 | Not started
Launch |  | 2015-10-09 | 2015-10-10 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team